## Overview
CanDoItAll WebGL + Economy Experiment Determinism Bundle v10
Bundle goal | Prepare deterministic experiment input + generic simulation/visualization foundations without building final demo.
Primary examples | Shared-well community, farmer-land anti-oligarchy probe
Components scope | Generic WebGL run/action/stage hardening; no economy terms; large-screen only
Economy scope | Experiment input pack, canonical scenario, typed refs, event taxonomy, simple transition engine readiness
Non-goal | No direct cross-repo bridge implementation
Hard rule | Codex must not create new branches
WebGL screen policy | Desktop/large-screen only; no small/medium/mobile/tablet optimization
Experiment policy | Randomization must produce versioned JSON inputs before simulation
Workflow inspiration | CanDoItAll bundle workflow: proof manifests, semantic invariants, closure audit
Main risk | Overfitting to shared-well and not building a reusable experimental kernel

## Implementation Matrix
SB | Repo | Project/Area | Priority | Dependency | Work summary | Bottleneck/Risk | Validation | Done artifact
SB01 | Cross-repo | Workflow/Proof | P0 | See subbundle dependency order | SB01 cross repo inventory and workflow gate | Scope drift or incomplete proof. | Build + tests + proof/SBxx manifests | proof/SB01/manifest.md
SB02 | Components | WebGlLib/WebGlRunLib | P0 | See subbundle dependency order | SB02 components ordered action stage contracts | Batch coalescing can destroy ordered actions. | Build + tests + proof/SBxx manifests | proof/SB02/manifest.md
SB03 | Components | WebGlLib/WebGlRunLib | P1 | See subbundle dependency order | SB03 components action normalization and alias policy | Scope drift or incomplete proof. | Build + tests + proof/SBxx manifests | proof/SB03/manifest.md
SB04 | Components | WebGlLib/WebGlRunLib | P1 | See subbundle dependency order | SB04 components target anchor distance resolver | Scope drift or incomplete proof. | Build + tests + proof/SBxx manifests | proof/SB04/manifest.md
SB05 | Components | WebGlLib/WebGlRunLib | P0 | See subbundle dependency order | SB05 components batching parity and performance | C# and JS batch semantics can drift. | Build + tests + proof/SBxx manifests | proof/SB05/manifest.md
SB06 | Components | WebGlLib/WebGlRunLib | P1 | See subbundle dependency order | SB06 components run document and input pack bridge contracts | Scope drift or incomplete proof. | Build + tests + proof/SBxx manifests | proof/SB06/manifest.md
SB07 | Components | WebGlLib/WebGlRunLib | P1 | See subbundle dependency order | SB07 components large screen runtime guard | Scope drift or incomplete proof. | Build + tests + proof/SBxx manifests | proof/SB07/manifest.md
SB08 | Economy | Simulation.* | P0 | See subbundle dependency order | SB08 economy experiment input pack contracts | Without input pack, experiments are not interpretable. | Build + tests + proof/SBxx manifests | proof/SB08/manifest.md
SB09 | Economy | Simulation.* | P0 | See subbundle dependency order | SB09 economy canonical scenario model and alias cleanup | Alias collections can drift and break hashes. | Build + tests + proof/SBxx manifests | proof/SB09/manifest.md
SB10 | Economy | Simulation.* | P0 | See subbundle dependency order | SB10 economy typed references and event taxonomy | Untyped references make event interpretation ambiguous. | Build + tests + proof/SBxx manifests | proof/SB10/manifest.md
SB11 | Economy | Simulation.* | P0 | See subbundle dependency order | SB11 economy parameter and placement json files | Hidden constants/randomization undermine reproducibility. | Build + tests + proof/SBxx manifests | proof/SB11/manifest.md
SB12 | Economy | Simulation.* | P1 | See subbundle dependency order | SB12 economy random input generation policy | Scope drift or incomplete proof. | Build + tests + proof/SBxx manifests | proof/SB12/manifest.md
SB13 | Economy | Simulation.* | P0 | See subbundle dependency order | SB13 economy generic state transition engine | Handwritten frames block real simulation. | Build + tests + proof/SBxx manifests | proof/SB13/manifest.md
SB14 | Economy | Simulation.* | P0 | See subbundle dependency order | SB14 economy shared well readiness without demo | Scope drift or incomplete proof. | Build + tests + proof/SBxx manifests | proof/SB14/manifest.md
SB15 | Economy | Simulation.* | P1 | See subbundle dependency order | SB15 economy farmer land generalization probe | Overfitting to shared-well. | Build + tests + proof/SBxx manifests | proof/SB15/manifest.md
SB16 | Economy | Simulation.* | P1 | See subbundle dependency order | SB16 economy visual action ordering and policy | Scope drift or incomplete proof. | Build + tests + proof/SBxx manifests | proof/SB16/manifest.md
SB17 | Cross-repo | Workflow/Proof | P1 | See subbundle dependency order | SB17 cross repo bridge design only | Scope drift or incomplete proof. | Build + tests + proof/SBxx manifests | proof/SB17/manifest.md
SB18 | Cross-repo | Workflow/Proof | P1 | See subbundle dependency order | SB18 performance and bottleneck proofs | Performance bottlenecks hidden until demo. | Build + tests + proof/SBxx manifests | proof/SB18/manifest.md
SB19 | Cross-repo | Workflow/Proof | P0 | See subbundle dependency order | SB19 bundle workflow proof and closure | Scope drift or incomplete proof. | Build + tests + proof/SBxx manifests | proof/SB19/manifest.md

## SharedWell Gaps
Capability | Current signal | Gap | Generic model needed | Priority | Example assertion
Explicit placement | Locations exist in scenario | Placement is not separate hashed input | SimulationPlacementDefinition JSON | P0 | Near actor distance < far actor distance
Parameter set | Some constants in factories | Carry/travel/tax/admin not externalized | SimulationParameterSetDefinition JSON | P0 | Carry capacity limits collected water
State transition engine | Frames are materialized by factory | Events do not yet drive all store changes | SimpleSimulationTransitionEngine | P0 | Event stream -> same frame hashes
Behavior/rule expansion | Rules exist mostly as refs | Rules do not generate tax/admin/enforcement events | BehaviorExpander + RulePolicy | P0 | Resale creates tax and admin events
Typed references | String source/target ids | Ambiguous actor/resource/location ids | SimulationRef | P0 | sourceKind+targetKind validate
Visual action order | Visual actions exist | Sequences can be duplicated/top-level drift | VisualActionNormalizer + stages | P0 | Move-use-admin-return ordered
Experiment provenance | Hashes exist for definitions | No input-pack hash manifest | ExperimentInputPack | P0 | Run result references all input hashes
Randomization discipline | Seed exists | Generated random values not persisted by contract | InputGenerator result JSON | P1 | Generator output reused exactly
Resale/trade model | Trade event kinds exist | No generic trade/tax/admin state handling | Trade/Tax/Admin event handlers | P1 | Nearby actor can sell surplus
Rule interpretation metrics | Issues/trust stores exist | No hypothesis/metric/invariant model | MetricDefinition + ExpectedInvariant | P1 | Ostrom/Smith-style interpretation

## FarmerLand Probe
Capability | Why it matters | Generic abstraction | Shared-well overlap | Needed proof
Finite spatial resource | Land is limited unlike water stock | ResourceKind=land-parcel/area + ownership | shared resource constraints | Input pack validates parcels
Expansion incentive | Farmers expand under external demand | investment/expansion events | resale incentive | Events can express expansion
External demand | Market may be unlimited or capped | ExternalDemandDefinition | far-household demand | Demand parameter affects outcomes
Anti-oligarchy rules | Prevent one actor owning all land | RuleDefinition + concentration metric | fair-draw / resale-tax | HHI/top-share invariant
Ownership transfer | Land changes hands | typed ref + store/asset ownership | water resale transfer | Transition engine updates ownership
Interpretation metrics | Need measurable outcome | MetricDefinition | trust/well-health metrics | Metrics generated from frames

## Input Pack Files
File | Purpose | Hash included | Generated allowed | Notes
experiment.json | Experiment identity/hypothesis/treatment | Yes | No | Top-level input pack manifest
scenario.definition.json | Actors/resources/locations/rules/events | Yes | No | Canonical normalized scenario
placement.json | Actual coordinates/topology | Yes | Yes, pre-run only | Random generator writes this file before run
parameters.json | Needs/capacity/travel/tax/admin/demand | Yes | Yes, pre-run only | Must be explicit for interpretability
institution.rules.json | Allocation, resale, tax, enforcement | Yes | No | Institution/treatment definition
run.plan.json | Backend, steps, output policy | Yes | No | No hidden random state
visual.mapping.json | Domain visual intentions to generic actions | Yes | No | No Components types in Economy
expected.invariants.json | Metrics and assertions | Yes | No | Avoid ‘looks interesting’ interpretation

## Validation Gates
Gate | Repo | Command/Proof | Pass condition | Large-screen rule
Branch guard | Both | git branch --show-current | No new branch created | N/A
Components build | Components | dotnet build CanDoItAll.Components.slnx | Success | N/A
Components tests | Components | WebGlLib + WebGlRunLib tests | Success | N/A
JS audit | Components | npm run webgllib:audit-scene-runtime | Success | No mobile/small/medium tasks
Economy build | Economy | dotnet build CanDoItAll.Economy.slnx | Success | N/A
Economy tests | Economy | dotnet test tests/CanDoItAll.Economy.Tests | Success | N/A
Boundary audit | Economy | .\scripts\audit-simulation-boundaries.ps1 | No forbidden refs | N/A
Input pack proof | Economy | JSON load/validate/hash tests | Stable hashes | N/A
Browser proof if used | Components | Playwright large viewport only | 1440x900+ | No mobile/tablet proof

## Performance Risks
Area | Risk | Threshold idea | Required test | Priority
Batching | Dropping staged motions | 0 dropped across different stages | Same object move->return fixture | P0
JS/C# parity | Normalizer drift | 0 diff in canonical fixtures | Shared JSON fixture | P0
Transition engine | Full frame rebuild per event | 100 actors x 50 steps under budget | Synthetic scenario | P1
Validation | O(n^2) refs | 1000 events validation bounded | Large input pack validator | P1
Visual mapper | List binding lookup | 1000 actions under budget | Dictionary binding test | P1
Ledger diff | Reprojecting full snapshots | changed stores only | 2 snapshots/1000 stores diff | P1
Render loop | Idle loop active unnecessarily | idle after no motion/symbol | Scheduler proof | P1
Asset cache | Template leak/disposal | dispose count stable | Repeated create/dispose proof | P1

## Source References
Repo | Path | Reason
Components | src/CanDoItAll.Components.WebGlRunLib/WebGlRunContracts.cs | Run/timeline/frame contracts
Components | src/CanDoItAll.Components.WebGlRunLib/WebGlRunActions.cs | Generic action/pose/symbol contracts
Components | src/CanDoItAll.Components.WebGlLib/WebGl/Interaction/WebGlSceneCommandBatch.cs | C# batch normalizer
Components | src/CanDoItAll.Components.WebGlLib/wwwroot/js/runtime/scene/26-webgl-scene-command-batch.js | JS batch application
Components | tools/webgllib/audit-scene-runtime.cjs | JS/large-screen/domain-neutral audit
Components | docs/webgl/large-screen-only-policy.md | WebGL desktop-only policy
Economy | src/CanDoItAll.Economy.Simulation.Abstractions/Scenario/SimulationScenarioDefinition.cs | Scenario definition
Economy | src/CanDoItAll.Economy.Simulation.Abstractions/Events/SimulationEvent.cs | Event model/taxonomy
Economy | src/CanDoItAll.Economy.Simulation.SimpleAccounts/SharedWellCommunityScenarioFactory.cs | Shared-well seed/readiness fixture
Economy | src/CanDoItAll.Economy.Simulation.Visualization/EconomyVisualActionMapper.cs | Event-to-visual-actions mapper
Main CanDoItAll | codex/skills/bundles/candoitall-bundle-workflow/SKILL.md | Workflow proof discipline